## ADaM
# Comment |  |  | NB: Columns A-F are formatted according to Status in column G (open/closed) |  |  | closed
Dataset | Comment by … | Comment Date | Comment | Team Review Date | Team Decision | Status | Comment
adae.xpt | Dante Di Tommaso | 2018-12-16 | TDF team replaced missing values with "N" for TRTEMFL "Treatment Emergent Analysis Flag". But other flags retain the "Y" or <null> codelist. Plus, the CDISC ADaM AE IG 1.0 (latest) specifies the "Y" codelist for TRTEMFL. Proposal: Restore the "Y"/<null> codelist to this flag - revert this change | 2019-01-25 | check, why P21 doesn't report this. Agreed to fix this (Jessica) | under review | Jessica: The ADAE.xpt I downloaded from Github had TRTEMFL with just Y values. Also, I looked up old pinnacle reports run on the original data, and it does have a finding when TRTEMFL flag value is not Y or null.
adcibc.xpt | Dante Di Tommaso | 2018-12-16 | the container "adcibc.xpt" still contains a dataset named "adqscibc". This should be "adcibc" (removing the qs) | 2019-01-25 | Agreed to fix (Jessica) | under review | Jessica: Updated file and uploaded to Github
adcibc.xpt | Dante Di Tommaso | 2018-12-16 | TDF team filled in 220 days for AWHI "Analysis Window Ending Timepoint" to uniformly close one-sided time windows. However, CDISC allow for one-sided time windows, and the TDF team have noted that Pinnacle 21 incorrectly flag these as errors. Proposal: • Revert this change, • preserve valid one-sided time window, • highlight this shortcoming of the Pinnacle 21 version available to TDF team | 2019-01-25 | Agreed to fix (Jessica) | under review | Jessica: Updated file and uploaded to Github
adlbc.xpt | Dante Di Tommaso | 2018-12-16 | DATETIME variables have lost the DATE9. format, which should be restored | 2019-01-25 | Agreed to fix (Peter) | under review | Peter: Updated file and uploaded to Github
adlbcpv.xpt | Dante Di Tommaso | 2018-12-16 | DATETIME variables have lost the DATE9. format, which should be restored | 2019-01-25 | Agreed to fix (Peter) | under review | Peter: Updated file and uploaded to Github
adlbh.xpt | Dante Di Tommaso | 2018-12-16 | DATETIME variables have lost the DATE9. format, which should be restored | 2019-01-25 | Agreed to fix (Peter) | under review | Peter: Updated file and uploaded to Github
adlbhpv.xpt | Dante Di Tommaso | 2018-12-16 | DATETIME variables have lost the DATE9. format, which should be restored | 2019-01-25 | Agreed to fix (Peter) | under review | Peter: Updated file and uploaded to Github
adnpix.xpt | Dante Di Tommaso | 2018-12-16 | TDF team deleted "0" values to create missing obs for AWTDIFF "Analysis Window Diff from Target", uniformly for specific "DERIVED" obs with: • PARAMCD = 'NPTOTMN', and • AWRANGE = '22 - 175' (QSSEQ is missing for these obs). However, in every instance, a "Diff from Target" of zero actually seems correct. Proposal: Restore these "0" values, revert the new missing values, or explain the justification of this change in the document | 2019-01-25 | (Peter) re-run P21 on original dataset. Track why we changed this. | open | Jessica: I looked up old pinnacle report, and looks like we made this change b/c of following error from pinnacle: Calculation issue: AWTDIFF is populated but AWTARGET and/or one of [ADY,ARELTM] are not both present and populated
adlbc.xpt | Dante Di Tommaso | 2018-12-16 | TDF team corrected missing value and formatting of AVISIT values |  |  | closed
adlbcpv.xpt | Dante Di Tommaso | 2018-12-16 | TDF team corrected missing value and formatting of AVISIT values |  |  | closed
adlbh.xpt | Dante Di Tommaso | 2018-12-16 | TDF team corrected missing value and formatting of AVISIT values |  |  | closed
adlbhpv.xpt | Dante Di Tommaso | 2018-12-16 | TDF team corrected missing value and formatting of AVISIT values |  |  | closed
adsl.xpt | Dante Di Tommaso | 2018-12-16 | TDF team renamed DCREASCD to DCSREAS, and created new EOSSTT "End of Study Status" column |  |  | closed
advs.xpt | Dante Di Tommaso | 2018-12-16 | TDF team created new BASETYPE "Baseline Type" column, and formatted "(beats/min)" for Pulse Rate to lower case |  |  | closed

## SDTM
# Comment |  |  | Columns A-F are formatted according to Status in column G (open/closed) |  |  | closed
Dataset | Comment by … | Comment Date | Comment | Team Review Date | Team Decision | Status
# Comment |  |  | Columns A-F are formatted according to Status in column G (open/closed) |  |  | open
# Comment |  |  | Columns A-F are formatted according to Status in column G (open/closed) |  |  | closed